REQUEST FOR OWNER’S REPRESENTATIVE SERVICES

LETTER OF INTEREST FOR CAPITOL HEAT & POWER PLANT REBUILD

DSF PROJECT #09 A 2 K

&

CHARTER STREET HEATING PLANT REBUILD

DSF PROJECT #09 A 2 L . 1

AGENCY:

Wisconsin Department of Administration & University of Wisconsin - Madison Campus

PLANT LOCATION:

Capitol Heat & Power Plant (“CHPP”)

624 East Main Street

Madison, Wisconsin 53703

Charter Street Heating Plant (“CSHP”)

University of Wisconsin – Madison Campus

117 North Charter Street

Madison, Wisconsin  53715

Introduction and Background:

The State of Wisconsin recently conducted a “Planning Study” for the main heating plants servicing the University of Wisconsin – Madison (“UW”) campus and other state office facilities.  This study was performed under State Project #08F2E by Titus:  Heating Plant Needs Alternative Analysis Based on Options with the Comprehensive Feasibility Study.

CHPP - One of the plants in the Planning Study was the Capitol Heat and Power Plant (“CHPP”) serving the Capitol complex and surrounding area. This plant provides steam, chilled water and electricity to heat, cool and power the Wisconsin State Capitol and eight other government buildings for a total of almost 3,000,000 SF. The plant’s two steam turbine generators provide between 2.5 and 3.0 megawatts (MW) to the capitol along with supplemental power from Madison Gas & Electric (“MG&E”).

CSHP - One of the plants in the Planning Study was the Charter Street Heating Plant (“CSHP”) serving the UW-Madison campus. This plant is the largest of three heating plants that delivers heating and cooling to the campus. CSHP also generates about 9 MW of electricity via a back pressure steam turbine generator that reduces the amount of electricity purchased from Madison Gas & Electric (“MG&E”).  The Planning Study was prompted to analyze the feasibility of alternatives to make necessary upgrades to or find technical and economically feasible alternatives to the coal-fired Charter Street Heating Plant (“CSHP”) boilers on the University of Wisconsin campus in Madison, Wisconsin.

The Planning Study was followed by a Comprehensive Heating Plant Study performed under Project #07E1U.  In the Comprehensive Heating Plant Study, thirteen options for the three existing state-owned heating plants and one potential, new combined heating plant were examined during the study.  These thirteen options were narrowed down to variations of two broad choices: implement separate upgrades to the CHPP and CSHP to meet current environmental compliance requirements and/or combine the needs from CHPP and CSHP into a single central facility, in partnership with or solely owned and operated by a third party. After the Comprehensive Heating Plant Study, the State decided to phase out the use of coal at the CHPP and CSHP and to increase fuel diversity primarily through inclusion of significant renewable biomass resources in the fuel mix at CSHP.

The final report of the Comprehensive Heating Plant Study, which details all plant options, can be accessed at: http://www.doa.state.wi.us/section.asp?linkid=146&locid=4.  Please review Volumes 2 and 3 for background and technical information on the CSHP and CHPP respectively.

The final report of the Planning Study will be posted on the same website in February.

Scope of Services:

The Owner’s Representative (“OR”), working with an Architect/Engineer (“A/E”) firm for CHPP and an Owner’s Engineer (“OE”)  for CSHP, will provide quality control, budget control, contract compliance, contractor coordination, billing review, project plan updates and timeline status, DSF decision support, expediting support, and on-site inspection services working closely with the OE.  These services will be handled by only one firm for both projects 09A2K and 09A2L but under separate contracts.

The Owner’s Representative will not direct or control any part of the OE’s or A/E’s work products nor take responsibility for the same.

Relationship Among Contractors:

The OE for CSHP and A/E firm for CHPP will provide complete conceptual design and/or project sequencing schedule, equipment technical specifications and detailed engineered drawings for Engineering Procurement Construction (EPC) Contractor and engineering support for all parties for CSHP and Contractor for CHPP.

The OE for CSHP and A/E firm for CHPP will provide technical specifications for environmental control equipment and stack dimensions, and assist in supporting a separate environmental engineering firm that is responsible for air permitting.

The OE for CSHP and A/E firm for CHPP will work with DSF and the Owner’s Representative to provide project management and control over the construction and EPC contractor for CSHP and Contractor for CHPP.

The EPC Contractor for CSHP and Contractor for CHPP will provide all equipment and materials procurement, construction, testing and completion activities.

See diagrams of organizational structure, also uploaded for this solicitation.

The selected Owner’s Representative must agree in writing to a “no conflicts” representation with other firms/contractors in all matters related to projects 09A2K and 09A2L including, but not limited to, the Owner’s Engineer, Architect/Engineer and any potential Contractor.  The Owner’s Representative is prohibited from becoming the Owner's Engineer, Architect/Engineer or joining with an OE or A/E to act as a subconsultant thereof.  The Owner’s Representative is also prohibited from bidding to become the EPC Contractor or Contractor or joining with a Contractor to act as a Subcontractor thereof.  The definition of "in writing" shall be a statement confirming the above on your company letterhead and submitted upon final selection with your fee proposal.

Project Deliverables:

      - Oversee work product of all parties associated with bringing these projects into compliance. Facilitate scheduled progress meetings as required by project phase through coordination of meetings and keeping meeting minutes.

      - Support DSF with the EPC Contractor contracting and procurement processes.

      - Function as the Owner’s Representative during the construction phase providing quality assurance oversight and completion of assigned WisBuild duties.

      - Provide monthly contract audit and compliance reports to the DSF.

      - Review progress and confirm completion of work associated with OE and EPC Contractor invoicing.

      - Keep current all planning and scheduling activities associated with the project.  To be updated monthly at a minimum dependant on project phase.

      - Provide issues management associated with design and/or construction conflicts which could have an effect on the project to DSF.

      - Provide oversight on all contracts associated with projects 09A2K and 09A2L such that all deliverables are in DSF’s hand before final payments can be released.

Project Timeline:

Key milestones for the CSHP project (09A2L) are as follow:

- Owner’s Engineer to start work by March 2, 2009.

- Owner’s Representative to begin work by April 1, 2009 (selected by DSF).

- Order new equipment by December 1, 2009.

- Owner’s Engineer to negotiate fixed or not to exceed pricing with DSF on remaining stages of engineering work by December 1, 2009.

- EPC Contractor to begin on-site work no later than March 15, 2010.

- Boiler delivery by March 1, 2011.

- Boiler commercial operation by December 1, 2012.

- Steam turbine generator delivery by December 1, 2012.

- Steam turbine generator, Boilers #1-4 work, and system efficiency projects completed and site clean-up on or before December 1, 2013.

Key milestones for the CHPP project (09A2K) are as follow:

- A/E Firm to start work by March 2, 2009.

- Bidding of major equipment (boilers and chillers) with bids released by March 26.

- Owner’s Representative to begin work by April 1, 2009 (selected by DSF).

- Bids due for new boilers and chillers April 23, 2009.

- Contractor to begin on-site work by August 1, 2009.

- Boiler and chiller delivery in staggered sequence beginning September 15, 2009.

- Complete 1500 ton electric chiller installation (separate project in progress) by October 2009.

- Project completion and site clean-up on or before November 1, 2010.

Skills and Knowledge:

A qualified firm would have a thorough knowledge, understanding and experience with the following:

- Brownfield, tri-generation (i.e., heating, cooling and electric) production plants and large scale industrial boiler and chiller installations.

- Knowledge of heating plant, chilled water production and electrical generation operational issues and design and technical considerations.

- Understanding of creative alternatives to expedite complex boiler, chiller and system efficiency projects.

- Experience in project management of rebuilding boilers and chillers in a plant during normal operations

- Knowledge of CFB/BFB boilers with a high capacity for biomass fuels.

- Knowledge of GAAP accounting principles.

- Knowledge of construction cost accounting and cost controls.

- Experience in budgeting, forecasting and variance to budget analysis.

- Experience in bringing a boiler project in a multiple team approach where an Owner’s Engineer and EPC contracting was involved.

Please indicate in your letter of interest your experience in these areas and include additional details pertaining to construction budget, schedule, size of project and when project was completed.

DOA Agency Contact:  Jay Ehrfurth, 608.266.5886, jay.ehrfurth@wisconsin.gov